## 18218
Product Name |  | ABABIL NG | TC Start Date | 23-10-2025 | TC Execution Start Date |  |  |  | TEST CASE STATUS |  | Severity |  | Priority
Event Name |  |  | TC End Date | 26-10-2025 | TC Execution End Date |  |  |  | PASS | 19 | Critical | 2 | High | 2
Para Form Name |  | Enhanced MTDR and SSP Account Closure Validations and Notifications | Test Case Developed By | Jannat |  |  |  |  | FAIL | 2 | High |  | Medium | 0
Developer Name (TL) |  |  | Test Case Reviewed By | Mahbub Hossain |  |  |  |  | NT | 0 | Medium | 0 | Low | 0
Test Executed by |  |  | MITS ID | 18218 |  |  |  |  | TOTAL | 21 | Low | 0 | Issue Accepted | 0
Req ID | Requirement Description | TC ID | Test Case Description | Category | Test Steps | Test Data | Expected Result | Actual Result | QA Status | Tested By | Severity | Priority | QA Remarks | Dev Status | Developed By | Dev Remarks | Updated QA Status | Update QA Remarks
Req_Id_001 | Enhanced MTDR and SSP Closure Validations and Notifications | TC_01 | Verify if new MTDR account with 0 transactions can be closed | UI | 1. Open new MTDR account 2. Attempt closure | 1. Account Number: 0021110000029 2. Account Balance = 0 | Closure eligible; eligibleForClose = TRUE | Error! Fixed deposit account not found.This account cannot be closed | FAIL |  | Critical | High | https://prnt.sc/c3X5ZOjRskJ7 |  |  |  | PASS | https://prnt.sc/fURNLc6ffmEO https://prnt.sc/_E3qc_gjSIo- After charge is settled to 0, the account is closed successfully https://prnt.sc/cybLemUU41mG https://prnt.sc/jgTHXqtUGuAq
|  | TC_02 | Verify closure after first transaction | UI | 1. Open new MTDR account 2. Perform first transaction 3. Attempt closure | 1. Account Number: 0021110000037 2. Account Balance = 10000 | Closure eligible if all validations pass; eligibleForClose = TRUE | This account is eligible for closure; Fixed deposit account closed successfully. Voucher no: 240403140361 | PASS |  |  |  | https://prnt.sc/LYB8s-p2A2_t |  |  |  | PASS | https://prnt.sc/Vc10tKvEQAFN
|  | TC_03 | Verify closure rejected for CLOSED account | UI | 1. Select MTDR account with status CLOSED 2. Attempt account closure | CLOSED Account number: 0021110000037 | Closure rejected; shows: “Account is already close | Account Status: Closed; Close button not visible; Reactivate button shown | PASS |  |  |  | https://prnt.sc/Aiv0xOr6go3j |  |  |  | PASS | https://prnt.sc/AaiAe_zCtepb
|  | TC_04 | Verify that a CLOSED account can be reactivated successfully | UI | 1. Select MTDR account with status CLOSED 2. Click Reactivate button 3. Confirm reactivation | CLOSED Account number: 0021110000037 | Account status changes to ACTIVATED; account is now eligible for closure | Fixed deposit account reactivated successfully | PASS |  |  |  | https://prnt.sc/_aNr-ARIfjjq |  |  |  | PASS | https://prnt.sc/oCS9nkHG8TbW
|  | TC_05 | Verify closure rejected for non-activated account | UI | 1. Select MTDR account not in ACTIVATED status 2. Attempt closure | INACTIVE Account number: 0021110000045 | Closure rejected; shows: “Account status is not activated.” | Account closing exception details show: “Account status is not activated | PASS |  |  |  | https://prnt.sc/_lay9DnqzvcP |  |  |  | PASS | https://prnt.sc/QS1i-1iHw_tr
|  | TC_06 | Verify closure blocked if account is frozen | UI | 1. Select frozen MTDR account 2. Attempt closure | Freeze flag = TRUE | Closure rejected; shows: “Account is frozen.” | Account closing exception details display: “Freeze status validation: Account is frozen | PASS |  |  |  | https://prnt.sc/8JNNxKQlO2qF |  |  |  | PASS | https://prnt.sc/R0t_sQr76KkK https://prnt.sc/cSPhhctkD_0O https://prnt.sc/SZtjFL9o28bh
|  | TC_07 | Verify closure blocked if lien amount > 0 | UI | 1. Select MTDR account with lien amount > 0 2. Attempt closure | 1. Account no: 0021110000045 2. Lien percentage = 100 | Closure rejected; shows: “Lien amount found in this account. | System displays in exception details: “Invalid", lien amount found in this account. | PASS |  |  |  | https://prnt.sc/kmyWmKXXwMXW https://prnt.sc/jfow68eCkR2t |  |  |  | PASS | https://prnt.sc/lx7uDBZfZsdH
|  | TC_08 | Verify closure blocked if quard amount > 0 | UI | 1. Select MTDR account with quard amount > 0 2. Attempt closure | 1. Account no: 0021110000037 2. Quard percentage = 100 | Closure rejected; shows: “Quard amount found in this account.” | System displays in exception details: “Invalid", Quard amount found in this account. | PASS |  |  |  | https://prnt.sc/taiyJP8HhGqu |  |  |  | PASS | https://prnt.sc/c0TkddfZgec-
|  | TC_09 | Branch Validation: Verify closure blocked if account branch ≠ user branch ( Configuration value = False) | UI | 1. User from branch A selects account from branch B 2. Attempt closure | 1. Account no: 0034020000013 (branch: 3) 2. User branch: 2 | Closure rejected; shows: “Cannot close account from different branch. | Close option not shown | PASS |  |  |  | https://prnt.sc/T8WqQ8dv8qTl |  |  |  | PASS | https://prnt.sc/YVgTLcEEuJa2
|  | TC_10 | Branch Validation: Verify closure blocked if account branch ≠ user branch ( Configuration value = True) | UI | 1. User from branch A selects account from branch B 2. Attempt closure | 1. Account no: 0034020000013 (branch: 3) 2. User branch: 2 | Closure rejected; shows: “Cannot close account from different branch. | System displays in exception details: “Invalid", Cannot close account from different branch. | PASS |  |  |  | https://prnt.sc/9BzbFwo4zEMO |  |  |  | PASS | https://prnt.sc/USRn9zwkPKSZ
|  | TC_11 | Verify system blocks closure when a CLOSED account ID is entered manually | UI | 1. Attempt to open account closure screen 2. Manually input an account number that is already CLOSED (or replace an active account ID with a closed one) | Account No (Closed): 0021110000052 | System displays error popup: “Account is closed | Error! 0021110000052 Account is closed. Exception log no :2621438 | PASS |  |  |  | https://prnt.sc/rfhdx-FJrECb |  |  |  | PASS | https://prnt.sc/VK92vjnKfcew
|  | TC_12 | Verify if new SSP account with 0 transactions can be closed | UI | 1. Open new SSP account 2. Attempt closure | 1. Account no: 0022220000016 2. Account Balance = 0 | Closure eligible; eligibleForClose = TRUE | Error! Recurring deposit account not found.This account cannot be closed | FAIL |  | Critical | High | https://prnt.sc/CXyx4VvsSBNu |  |  |  | PASS | https://prnt.sc/EV4wdCG-8BRD https://prnt.sc/mYpbvYMOqvRk After charge is settled to 0, the account is closed successfully https://prnt.sc/cZJTHgqjUbcA
|  | TC_13 | Verify closure after first transaction | UI | 1. Open new SSP account 2. Perform first transaction 3. Attempt closure | 1. Account no: 0022220000032 2. Account Balance = 2500 | Closure eligible if all validations pass; eligibleForClose = TRUE | Recuring deposit account closed successfully. Voucher no: 240403140386 | PASS |  |  |  | https://prnt.sc/KbbneClhx5-I |  |  |  | PASS | https://prnt.sc/ch1RZqq8vllh
|  | TC_14 | Verify closure rejected for CLOSED account | UI | 1. Select SSP account with status CLOSED 2. Attempt account closure | CLOSED Account number: 0022220000032 | Closure rejected; shows: “Account is already closed.” | Account Status: Closed; Close button not visible; Reactivate button shown | PASS |  |  |  | https://prnt.sc/Hz3TBTV6UrmD |  |  |  | PASS | https://prnt.sc/a58xyE-NsmBt
|  | TC_15 | Verify that a CLOSED account can be reactivated successfully | UI | 1. Select SSP account with status CLOSED 2. Click Reactivate button 3. Confirm reactivation | CLOSED Account number: 0022220000032 | Account status changes to ACTIVATED; account is now eligible for closure | Recurring deposit account reactivated successfully | PASS |  |  |  | https://prnt.sc/wxyqEZV0iN5B |  |  |  | PASS | https://prnt.sc/CgKUAdh1BKDS
|  | TC_16 | Verify closure rejected for non-activated account | UI | 1. Select SSP account not in ACTIVATED status 2. Attempt closure | Account status = INACTIVE | Closure rejected; shows: “Account status is not activated.” | Account closing exception details show: “Account status is not activated | PASS |  |  |  | https://prnt.sc/G7PUElAw8BDN |  |  |  | PASS | https://prnt.sc/NhlQKrZwGwUE
|  | TC_17 | Verify closure blocked if account is frozen | UI | 1. Select frozen SSP account 2. Attempt closure | 1. Account no: 0022220000049 ; Freeze flag = TRUE | Closure rejected; shows: “Account is frozen.” | Account closing exception details display: “Freeze status validation: Account is frozen" | PASS |  |  |  | https://prnt.sc/I0MVblWSd-E1 |  |  |  | PASS | https://prnt.sc/CeNmvmDkUcKU https://prnt.sc/pHweUCA12zaq
|  | TC_18 | Verify closure blocked if branch mismatch ( Configuration value = False) | UI | 1. User from branch A selects account from branch B 2. Attempt closure | Account branch ≠ User branch | Closure rejected; shows: “Cannot close account from different branch.” | Close option not shown | PASS |  |  |  | https://prnt.sc/Gpw0QWp7dSzf |  |  |  | PASS | https://prnt.sc/30iysrse4AcV
|  | TC_19 | Verify closure blocked if branch mismatch ( Configuration value =True) | UI | 1. User from branch A selects account from branch B 2. Attempt closure | 1. Account no: 0022220000032 (branch: 2) 2. User branch: 3 | Closure rejected; shows: “Cannot close account from different branch. | System displays in exception details: “Invalid", Cannot close account from different branch. | PASS |  |  |  | https://prnt.sc/0Q_ChcsRChub |  |  |  | PASS | https://prnt.sc/kkXRRyw8lPkM
|  | TC_20 | Verify closure blocked if lien amount > 0 | UI | 1. Select SSP account with lien amount > 0 2. Attempt closure | Lien percentage = 100 | Closure rejected; shows: “Lien amount found in this account. | System displays in exception details: “Invalid", lien amount found in this account. | PASS |  |  |  | https://prnt.sc/mseMiu__ONs_ https://prnt.sc/smgO3KxiVK8F |  |  |  | PASS | https://prnt.sc/kHETHzPNjmkP https://prnt.sc/SohpSUmEKtjP
|  | TC_21 | Verify system blocks closure when a CLOSED account ID is entered manually | UI | 1. Attempt to open account closure screen 2. Manually input an account number that is already CLOSED (or replace an active account ID with a closed one) | Account No (Closed): 0022220000024 | System displays error popup: “Account is closed | Error! 0022220000024 Account is closed. Exception log no :2621440 | PASS |  |  |  | https://prnt.sc/JSWW43P3LNka |  |  |  | PASS | https://prnt.sc/j1GHZ8hfpTJI
|  | TC_22 | Verify closure eligibility when Auto Standing Instruction is selected automatically | UI | 1. Select account with Auto Standing Instruction selected automatically. 2. Attempt to close the account. 3. Observe system response | Account No: 0027770000076 | Account closed successfully. | As per validation, account closed successfully after checking SI configuration | [8 empty] | PASS | https://prnt.sc/PLsOsjKP69Xa https://prnt.sc/z74M19clvNnp https://prnt.sc/P185YFzGSIJy

## 18363
Product Name |  | ABABIL NG | TC Start Date |  |  | TC Execution Start Date |  |  |  | TEST CASE STATUS |  | Severity |  | Priority
Event Name |  |  | TC End Date |  |  | TC Execution End Date |  |  |  | PASS | 81 | Critical | 0 | High | 0
Para Form Name |  | The payout file generation UI requires the financing account number as a new searching parameter. | Test Case Developed By | Jannat | [5 empty] | FAIL | 0 | High | 0 | Medium | 0
Developer Name (TL) |  |  | Test Case Reviewed By | [6 empty] | NT | 0 | Medium | 0 | Low | 0
Test Executed by |  |  | MITS ID | 18363 | [5 empty] | TOTAL | 81 | Low | 0 | Issue Accepted | 0
Req ID | Requirement Description | TC ID | Test Case Description | Category | Automation TC ID | Test Steps | Test Data | Expected Result | Actual Result | QA Status | Tested By | Severity | Priority | QA Remarks | Dev Status | Developed By | Dev Remarks | Updated QA Status
Req_ID_01 | Payout file generation UI requires the financing account number as a new searching parameter | TC-001 | Verify that Date, Event Type, and Payment Method are mandatory fields for a search. | UI |  | 1. Navigate to Payment File Generation UI. 2. Click the 'Search' button without selecting any criteria. | Date: Blank, Event Type: Blank, Payment Method: Blank | System should display an error message prompting the user to select mandatory fields (Date, Event Type, Payment Method). | Error! Search Form is invalid. | PASS |  |  |  | https://prnt.sc/rAtENUYYnnfz
|  | TC-002 | Verify search is restricted with only Date and Event Type | UI |  | 1. Enter Date. 2. Select Event Type: Fixed Deposit Closing. 3. Click Search. | Payment Method field: Blank. | Error message regarding the missing Payment Method should be displayed | Payment method is required | PASS |  |  |  | https://prnt.sc/nY4CcT8mA7-I
|  | TC-003 | Verify search is restricted with only Date and Payment method | UI |  | 1. Enter Date. 2. Select Payment method. 3. Click Search. | Event Type field: Blank | Error message regarding the missing Event type should be displayed | Event Type is required | PASS |  |  |  | https://prnt.sc/JO3nbGtImoch
|  | TC-004 | Verify search is restricted with only Event type and Payment method | UI |  | 1. Select Payment method and Event type. 3. Click Search. | Date field: Blank | Error message regarding the missing Dateshould be displayed | Date is required | PASS |  |  |  | https://prnt.sc/ALr_tU75xIfn
|  | TC-005 | Verify search for FD Closing using BEFTN | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Date: 04-04-2024, Event Type: FD Closing, Payment Method: BEFTN. | Multiple records (at least those associated with Shadow A/C and A/C no should be displayed in the Account Information table. | Account Information displayed successfully.The grid populated with accurate data:- Shadow Account No: 0023010000208 & 0025020000268 Account No: 0021010000574 and 0021110000094 | PASS |  |  |  | https://prnt.sc/13ZM3kZVysya
|  | TC-006 | Verify search for FD Closing using Pay Order. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: FD Closing, Payment Method: Pay Order. | Records should be displayed | Account Information displayed successfully.The grid populated with accurate data:- Shadow Account No: 0025020000268 & 0023010000208 Account No: 0021110000136 and 0027110000034 | PASS |  |  |  | https://prnt.sc/906qcgyJPX9F
|  | TC-007 | Verify search for FD Closing using RTGS. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: FD Closing, Payment Method: RTGS. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/guSnLup_SMNC
|  | TC-008 | Verify search for FD Closing using Cheque. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: FD Closing, Payment Method: Cheque. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/bCleIdy9DMkG
|  | TC-009 | Verify search for FD Closing using Transfer. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: FD Closing, Payment Method: Transfer. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/dCCmQUvDKFr3
|  | TC-010 | Verify search/filter using Shadow Account Number for FD Closing Account. | UI |  | 1. Enter Shadow Account No 2. Click Search button. | Event/Payment: FD Closing/BEFTN, Shadow A/C: 0023010000208, 0025020000268 | The Account Information table should display only the records linked to Shadow Account No 0025020000268. | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/tz7SeCXoAsLv https://prnt.sc/fcY5H4jA4QLk
|  | TC-011 | Verify search/filter using Account Number (Financing A/C) for FD Closing Account. | UI |  | 1. Enter Account No. 2. Click the Search icon next to the Account Number field. | Event/Payment: FD Closing/BEFTN, Account No: 0021010000574 and 0021110000094 . | The Account Information table should display one single record corresponding exactly to Account No | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/GWAtqsPiUpPC https://prnt.sc/uNTZ7il9SAYp
|  | TC-012 | Verify search/filter using both Account Number and shadow account (Financing A/C) for FD Closing Account. | UI |  | 1. Enter Account No. 2. Enter Shadow No. 3. Click the Search icon next to the Account Number field. | Event/Payment: FD Closing/BEFTN, Account No: 0021110000094 Shadow No: 0025020000268 | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/YzSOHt4fxCx6
|  | TC-013 | Verify the error handling when searching with a unique, non-existent, or mismatched record combination for FD Closing Account. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Enter Shadow Account number. 5. Enter Account number. 6. Click the Search button. | Date: 04-04-2024, Event Type: FD Closing, Payment Method: BEFTN, Shadow No: 0025020000268, Account No: 0021010000574. | The "No records found" message should appear below the table. | Account not found for Fixed Deposit Closing | PASS |  |  |  | https://prnt.sc/0afdztOJBlGF
|  | TC-014 | Verify mandatory fields for Generate File option (Select Bank and Select Account). | UI |  | 1. Execute a successful search (e.g., FD Closing/BEFTN) to retrieve records. 2. Do NOT select values for "Select Bank" or "Select Account". 3. Click the Generate File button. | Records selected, Select Bank: Blank, Select Account: Blank. | The system must display: Error! Form is invalid | Error! Form is invalid. | PASS
|  | TC-015 | Verify Generate File functionality for FD Closing payout via RTGS | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method: RTGS. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Fixed Deposit Closing, 3. Payment Method: RTGS, Records: All retrieved. | RTGS file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully RTGS, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/nrvr7EZcZdQh https://prnt.sc/wTBJZB9fkvTC https://prnt.sc/uCeS57I8hlHY
|  | TC-016 | Verify Generate File functionality for FD Closing payout via Transfer | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method: Transfer. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Fixed Deposit Closing, 3. Payment Method: Transfer, Records: All retrieved. | BEFTN file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully Transfer, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/JiI-ohbcC5-Q https://prnt.sc/h76j1TohhR-r
|  | TC-017 | Verify the system prevents bulk actions (Generate File / Stop Payment) if no records are selected |  |  | 1. Event Type: Recurring Deposit Closing, Payment Method: Transfer. 2. Select valid values for Select Bank and Select Account. 3. Do NOT select any records from the Account Information table checkboxes. 4. Click the Generate File button (or Stop Payment button). | Event Type: FD Closing, Payment Method: Transfer, Select Bank/Account: Valid, Records: None selected | The system must immediately display an error message clearly indicating that records must be selected before proceeding (matching the observed "Please select account information first" message). | Error! Please select account information first. (Generate File) Error! Please select payment information first. (Stop payment) | PASS |  |  |  | https://prnt.sc/NtcLUXmA1xpn https://prnt.sc/38PyuzIXXy9Q
|  | TC-018 | Verify mandatory fields for Do Transaction option | UI |  | 1. Search: Event Type, Payment Method. 2. Do NOT select values for "Select Bank" or "Select Account". 4. Click the Do Transaction button. | Records selected, Select Bank: Blank, Select Account: Blank. | The system must display: Error! Form is invalid | "Error! Form is invalid." | PASS |  |  |  | https://prnt.sc/N5JvrEvMUjBK
|  | TC-019 | Verify successful execution of Do Transaction for selected records using the Pay Order method. | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | Event Type: FD Closing, Payment Method: Pay Order, Records: Selected, Bank/Account: Valid source selected. | The system should display a success message (e.g., "Transaction completed successfully"). | Transaction Sucessfully | PASS |  |  |  | https://prnt.sc/P62WZ-A1soRR https://prnt.sc/yptp0DaJ12U-
|  | TC-020 | Verify Stop Payment for selected records. | UI |  | 1. Execute to retrieve records. 2. Select records using the checkboxes. 3. Click the Stop Payment button. |  | The selected records should be processed for Stop Payment. | Success! Payment Stopped Successfully | PASS |  |  |  | https://prnt.sc/-A8zhQApyOcj
|  | TC-021 | Verify search for Recurring Deposit Closing using Transfer. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: RD Closing, Payment Method: Transfer | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/zyDaHnDom09U
|  | TC-022 | Verify search for RD Closing using BEFTN | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Date: Valid, Event Type: RD Closing, Payment Method: BEFTN. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/NBBShWnvLzAr
|  | TC-023 | Verify search for RD Closing using RTGS | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Date: Valid, Event Type: RD Closing, Payment Method: RTGS. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/gUvbipcfvari
|  | TC-024 | Verify search for RD Closing using Cheque | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Date: Valid, Event Type: RD Closing, Payment Method: Cheque. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/Xlq35r9US_wu
|  | TC-025 | Verify search for RD Closing using Pay order | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Date: Valid, Event Type: RD Closing, Payment Method:Pay order. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/p_5DcuTyM6c_
|  | TC-026 | Verify search/filter using Shadow Account Number for RD Closing Account. | UI |  | 1. Enter Shadow Account No 2. Click Search button. | Event/Payment: RD Closing/Cheque, Shadow A/C: 0023010000208, 0025020000268 | The Account Information table should display only the records linked to Shadow Account No 0023010000208 . | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/__NmrNFR-96D https://prnt.sc/mvFcA2EzMt0Y
|  | TC-027 | Verify search/filter using Account Number (Financing A/C) for RD Closing Account | UI |  | 1. Enter Account No. 2. Click the Search icon next to the Account Number field. | Event/Payment: RD Closing/Pay order, Account No: 0022110000068 and 0027770000109. | The Account Information table should display one single record corresponding exactly to Account No | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/P_QcOy-mgkuw https://prnt.sc/w8xvbtBoHRlc
|  | TC-028 | Verify search/filter using both Account Number and shadow account (Financing A/C) for RD Closing Account. | UI |  | 1. Enter Account No. 2. Enter Shadow No. 3. Click the Search icon next to the Account Number field. | Event/Payment: RD Closing/BEFTN, Account No: 0027770000126 Shadow No: 0023010000208 | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/va_5SC7ntQ36
|  | TC-029 | Verify the error handling when searching with a unique, non-existent, or mismatched record combination for RD Closing Account. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Enter Shadow Account number. 5. Enter Account number. 6. Click the Search button. | Date: 04-04-2024, Event Type: FD Closing, Payment Method: RTGS, Shadow No: 0023010000208, Account No: 0027770000084 | The "No records found" message should appear below the table. | Account not found for Recurring Deposit Closing | PASS |  |  |  | https://prnt.sc/pw2UoDEEN2ug
|  | TC-030 | Verify Generate File functionality for RD Closing payout via BEFTN | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method: BEFTN. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Recurring Deposit Closing, 3. Payment Method: BEFTN, Records: All retrieved. | BEFTN file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully BEFTN, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/rdckBfHhB7mH https://prnt.sc/eoHKoGOTq-Af
|  | TC-031 | Verify Generate File functionality for RD Closing payout via RTGS | UI |  | 1. Search for Records: Enter Date, select Event Type and select Payment Method 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Recurring Deposit Closing, 3. Payment Method: RTGS, Records: All retrieved. | RTGS file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully RTGS, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/wKKFzHtYLhTT https://prnt.sc/eXaTDC6SXi3a https://prnt.sc/H0PykPiCVEPe
|  | TC-032 | Verify successful execution of Do Transaction for selected records using the Cheque method. | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | Event Type: RD Closing, Payment Method: Cheque, Records: Selected, Bank/Account: Valid source selected. | The system should display a success message (e.g., "Transaction completed successfully"). |  | PASS |  |  |  | https://prnt.sc/qgbnKSihVmzh https://prnt.sc/FXcLB9fnnW7I
|  | TC-033 | Verify Stop Payment for selected records. | UI |  | 1. Execute to retrieve records. 2. Select records using the checkboxes. 3. Click the Stop Payment button. |  | The selected records should be processed for Stop Payment. | Success! Payment Stopped Successfully | PASS |  |  |  | https://prnt.sc/0JRRMJFAnjzo https://prnt.sc/mNrs1MKQT9sn
|  | TC-034 | Verify search for Withdrawal Advice using Pay Order. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: Withdrawal Advice, Payment Method: Pay Order. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/IQcGpinTv1YZ
|  | TC-035 | Verify search for Withdrawal Advice using Cheque. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: Withdrawal Advice, Payment Method: Cheque. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/KVGtX32IrayU
|  | TC-036 | Verify search for Withdrawal Advice using Transfer. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: Withdrawal Advice, Payment Method: Transfer. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/6Ff-Ka2-zwFR
|  | TC-037 | Verify search for Withdrawal Advice using RTGS. | UI |  | 1. Enter Date. 2. Select Event Type. 3. Select Payment Method. 4. Click Search. | Event Type: Withdrawal Advice, Payment Method: RTGS. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/5u9vmfziLfRV
|  | TC-038 | Verify search for Withdrawal Advice using BEFTN. | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: Withdrawal Advice, Payment Method: BEFTN. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/OtQ1K26Twz1d
|  | TC-039 | Verify search/filter using Shadow Account Number for Withdrawal Advice Account. | UI |  | 1. Enter Shadow Account No 2. Click Search button. | Event/Payment: Withdrawal Advice/BEFTN, Shadow A/C: 0025020000268; 0023010000208 | The Account Information table should display only the records linked to Shadow Account No 0025020000268. | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/hBssXsdO7ZcG https://prnt.sc/XlgfHPV7rZgp
|  | TC-040 | Verify search/filter using Account Number (Financing A/C) for Withdrawal Advice Account. | UI |  | 1. Enter Account No. 2. Click the Search icon next to the Account Number field. | Event/Payment: Withdrawal Advice /BEFTN, Account No: 0027110000018 and 0021010000566 . | The Account Information table should display one single record corresponding exactly to Account No | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/DkigTdDuUW7P https://prnt.sc/T0o-o5hH8zks
|  | TC-041 | Verify search/filter using both Account Number and shadow account (Financing A/C) for Withdrawal Advice Account. |  |  | 1. Enter Account No. 2. Enter Shadow No. 3. Click the Search icon next to the Account Number field. | Event/Payment: Withdrawal Advice /Transfer, Account No: 0021010000566; 0021010000566 Shadow No: 0025020000268; 0023010000208 | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/nSCP-kOMwH6u https://prnt.sc/mcLpaABTkp1S
|  | TC-042 | Verify the error handling when searching with a unique, non-existent, or mismatched record combination for Withdrawal Advice. | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Enter Shadow Account number 5. Enter Account number. 6. Click the main Search button | Date: 04-04-2024, Event Type: Withdrawal Advice, Payment Method: Cheque, Shadow No: 0023010000208, Account No: 0027110000018. | The table should show "No records found. | An Info! pop-up message is displayed: "Account not found for Withdrawal Advice". The table remains empty. | PASS |  |  |  | https://prnt.sc/BDbCUzF5ka6E
|  | TC-043 | Verify Generate File functionality for Withdrawal Advice payout via BEFTN | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method: BEFTN. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Withdraw advice, 3. Payment Method: BEFTN, Records: All retrieved. | BEFTN file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully BEFTN, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/66tXa3aKYpyI https://prnt.sc/0O8DZuUeHtzk https://prnt.sc/4GYU4gzCJnss
|  | TC-044 | Verify Generate File functionality for Withdrawal Advice payout via Transfer | UI |  | 1. Search for Records: Enter Date, select Event Type and select Payment Method. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Withdraw advice, 3. Payment Method: Transfer, Records: All retrieved. | Transfer file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully Transfer, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/KtNTGGtNAMCT https://prnt.sc/SxbrGyhRQeL4 https://prnt.sc/rH1chUhV86Em
|  | TC-045 | Verify Do transcation File functionality for Withdrawal Advice payout via Pay Order | UI |  | 1. Search for Records: Enter Date, select Event Type, and select Payment Method. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Withdraw advice, 3. Payment Method: Pay order, Records: All retrieved. | Transcation (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully Transfer, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/VbM0Fns4x6U6 https://prnt.sc/6Vuxcyqg35_v
|  | TC-046 | Verify Stop Payment for selected records. | UI |  | 1. Execute to retrieve records. 2. Select records using the checkboxes. 3. Click the Stop Payment button. |  | The selected records should be processed for Stop Payment. | Success! Payment Stopped Successfully | PASS |  |  |  | https://prnt.sc/xlrLb_bWwbwX https://prnt.sc/Ir7LR8ixtiRJ
|  | TC-047 | Verify search for CASA Refund using Pay Order | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: CASA Refund, Payment Method: Pay Order. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/Y_sA9LutXBSV
|  | TC-048 | Verify search for CASA Refund using Cheque | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: CASA Refund, Payment Method: Cheque. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/UE07op5InhoQ
|  | TC-049 | Verify search for CASA Refund using Transfer | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: CASA Refund, Payment Method: Transfer. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/Pdn8bdH6vECz
|  | TC-050 | Verify search for CASA Refund using RTGS | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: CASA Refund, Payment Method: RTGS. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/AwS5S4YMFPPw
|  | TC-051 | Verify search for CASA Refund using BEFTN | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: CASA Refund, Payment Method: BEFTN. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/3BBSpvYUHFpm
|  | TC-052 | Verify search/filter using Shadow Account Number for CASA Refund Account. | UI |  | 1. Enter Shadow Account No 2. Click Search button. | Event/Payment: Withdrawal Advice/BEFTN, Shadow A/C:0025020000409; 0023010000026 | The Account Information table should display only the records linked to Shadow Account No | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/3BBSpvYUHFpm https://prnt.sc/t7rIwJAc9gF3
|  | TC-053 | Verify search/filter using Account Number (Financing A/C) for CASA Refund Account | UI |  | 1. Enter Account No. 2. Click the Search icon next to the Account Number field. | Event/Payment: Withdrawal Advice /BEFTN, Account No: 0023010000026 and 0025020000409. | The Account Information table should display one single record corresponding exactly to Account No | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/nbKOhtYo1XeH https://prnt.sc/NmVXTyk061De
|  | TC-054 | Verify search/filter using both Account Number and shadow account (Financing A/C) for CASA Refund Account. |  |  | 1. Enter Account No. 2. Enter Shadow No. 3. Click the Search icon next to the Account Number field. | Event/Payment: Withdrawal Advice /BEFTN, Account No: 0025020000409 ; 0023010000026. Shadow No: 0025020000409 ; 0023010000026. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/l1LE6kEJ8C0y
|  | TC-055 | Verify search/filter using both Account Number and shadow account (Financing A/C) for CASA Refund Account. |  |  | 1. Enter Account No. 2. Enter Shadow No. 3. Click the Search icon next to the Account Number field. | Event/Payment: Withdrawal Advice /Transfer, Account No: 0021010000566; 0021010000566 Shadow No: 0025020000268; 0023010000208 | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/nSCP-kOMwH6u https://prnt.sc/mcLpaABTkp1S
|  | TC-056 | Verify the error handling when searching with a unique, non-existent, or mismatched record combination for CASA Refund Account. | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Enter Shadow Account number 5. Enter Account number. 6. Click the main Search button | Date: 04-04-2024, Event Type: CASA Refund, Payment Method: RTGS, Shadow No: 0023010000208, Account No: 0023010000067. | The table should show "No records found. | Account not found for Refund | PASS |  |  |  | https://prnt.sc/VL8cZKNm2Oz3
|  | TC-057 | Verify Generate File functionality for CASA Refund payout via BEFTN | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method: BEFTN. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: CASA Refund, 3. Payment Method: BEFTN, Records: All retrieved. | BEFTN file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully BEFTN, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/bR5B3tPD_hNV https://prnt.sc/WzocYMcRpAJo https://prnt.sc/PK-ENICXzm49
|  | TC-058 | Verify DO Transaction functionality for CASA Refund payout via Cheque | UI |  | 1. Search for Records: Enter Date, select Event Type, and select Payment Method. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Click Do transcation button. 5. Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: CASA Refund, 3. Payment Method: Cheque, Records: All retrieved. | Transaction should be successfully generated and downloaded | As Expected | PASS |  |  |  | https://prnt.sc/yIPFnJTUzjmk https://prnt.sc/VgEBIG_RgRhH
|  | TC-059 | Verify Stop Payment for selected records. | UI |  | 1. Execute to retrieve records. 2. Select records using the checkboxes. 3. Click the Stop Payment button. |  | The selected records should be processed for Stop Payment. | Success! Payment Stopped Successfully | PASS |  |  |  | https://prnt.sc/k5Z3DgV9-Kpu
|  | TC-060 | Verify search for Investment Disbursement using RTGS | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: Investment Disbursement, Payment Method: RTGS. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/_bdXD55H3xvv
|  | TC-061 | Verify search for Investment Disbursement using Cheque | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: Investment Disbursement, Payment Method: Cheque. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/kUvjyu9I2jsk
|  | TC-062 | Verify search for Investment Disbursement using BEFTN | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: Investment Disbursement, Payment Method: BEFTN. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/FBX2k8w1sOm5
|  | TC-063 | Verify search for Investment Disbursement using Pay Order | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Click Search. | Event Type: Investment Disbursement, Payment Method: Pay Order. | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/FBX2k8w1sOm5
|  | TC-064 | Verify search/filter using Shadow Account Number for Investment Disbursement. | UI |  | 1. Enter Shadow Account No 2. Click Search button. | Event/Payment: Investment Disbursement/RTGS, Shadow A/C: 0025020000011 | The Account Information table should display only the records linked to Shadow Account No 0025020000011 | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/oEbC_RmieOL6 https://prnt.sc/XtpdvZZ0lh1O https://prnt.sc/1UAGq9BxXUS0 https://prnt.sc/hg82IaexmVib
|  | TC-065 | Verify search/filter using Account Number (Financing A/C). | UI |  | 1. Execute TC-S-002 to get a result set. 2. Enter Account No. 3. Click the Search) icon next to the Account Number field. | Event/Payment: Investment Disbursement./Pay Order, Account No: 0025070000051 | The Account Information table should display one single record corresponding exactly to Account No 0025070000051 | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/Xpg3pgIC18Y6 https://prnt.sc/TMbdIB-zA3cM https://prnt.sc/cNrN9mReCEbg https://prnt.sc/72jNA-3fDALh
|  | TC-066 | Verify search/filter using both Account Number and shadow account (Financing A/C) for Investment Disbursement. | UI |  | 1. Enter Account No. 2. Enter Shadow No. 3. Click the Search icon next to the Account Number field. | Event/Payment: Investment Disbursement /RTGS, Account No: 0022030000123; 0025070000044. Shadow No: 0025020000011 | Records should be displayed | Account Information displayed successfully. | PASS |  |  |  | https://prnt.sc/FSVcbf1EwIGl https://prnt.sc/B4GsYMNqRITs
|  | TC-067 | Verify the error handling when searching with a unique, non-existent, or mismatched record combination for Investment Disbursement. | UI |  | 1. Enter Date. 2. Select Event Type 3. Select Payment Method 4. Enter Shadow Account number 5. Enter Account number. 6. Click the main Search button | Date: 04-04-2024, Event Type: CASA Refund, Payment Method: RTGS, Shadow No: 0025020000094, Account No: 0022030000123 | The table should show "No records found. | Account not found for Refund | PASS |  |  |  | https://prnt.sc/R9JIopydC5S4
|  | TC-068 | Verify the system prevents bulk actions (Generate File / Stop Payment) if no records are selected. | UI |  | 1. Execute a successful search: Event Type; Payment Method. 2. Select valid values for Select Bank and Select Account. 3. Do NOT select any records from the Account Information table checkboxes. 4. Click the Generate File button (or Stop Payment button). | Event Type: Investment Disbursement, Payment Method: RTGS, Select Bank/Account: Valid, Records: None selected. | The system must immediately display the error message: "Error! Please select account information first." | Error! Please select account information first. | PASS |  |  |  | https://prnt.sc/EtCfUN4E_8fp https://prnt.sc/RZp32NFLqdoO
|  | TC-069 | Verify Generate File functionality for Investment Disbursement payout via RTGS | UI |  | 1. Search for Records: Enter Date, select Event Type: Fixed Deposit Closing, and select Payment Method: RTGS. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Generate File: Click the Generate File button. 5. Confirm Action: Confirm the action | 1. Date: Valid (04-04-2024), 2. Event Type: Investment Disbursement, 3. Payment Method: RTGS, Records: All retrieved. | RTGS file (e.g., CSV/Excel file) should be successfully generated and downloaded | Sucessfully RTGS, CSV file generated and downloaded. | PASS |  |  |  | https://prnt.sc/o9BeOcdAK2Vg https://prnt.sc/9JMxUfg3CxE0 https://prnt.sc/_04G3Uc3o8Pc https://prnt.sc/KQ0FCZ2wYoWK
|  | TC-070 | Verify DO Transaction functionality for Investment Disbursement payout via Cheque | UI |  | 1. Search for Records: Enter Date, select Event Type, and select Payment Method. 2. Click the Search button. 3. Select Records: Select ALL retrieved records using the header checkbox. 4. Click Do transcation button. 5. Confirm the action | 1. Date: Valid (03-04-2024), 2. Event Type: Investment Disbursement, 3. Payment Method: Cheque, Records: All retrieved. | Transaction should be successfully generated and downloaded | As Expected | PASS |  |  |  | https://prnt.sc/WKRSwBGWx1YP https://prnt.sc/qWj1QwOxFvrf
|  | TC-071 | Verify Stop Payment for selected records. | UI |  | 1. Execute to retrieve records. 2. Select records using the checkboxes. 3. Click the Stop Payment button. |  | The selected records should be processed for Stop Payment. | Success! Payment Stopped Successfully | PASS |  |  |  | https://prnt.sc/wtnZfLjAWH1M https://prnt.sc/86LkYE3GQ2fu
|  | TC-072 | Verify search for Profit Withdraw using BEFTN | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/cxZ__4SkjjL2
|  | TC-073 | Verify search for Profit Withdraw using RTGS | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/iqe3GIxfZDqq
|  | TC-074 | Verify search for Profit Withdraw using Transfer | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/eamUkSMhKGjg
|  | TC-075 | Verify search for Profit Withdraw using Cheque | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/72zApCcQKk94
|  | TC-076 | Verify search for Profit Withdraw using Pay order | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/SupyNswNbww3
|  | TC-077 | Verify Generate File functionality for Profit Withdraw payout via BEFTN | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/ibRXN_VcpujL https://prnt.sc/15DNwi9ZGtii https://prnt.sc/GyiumVSnQ0pW
|  | TC-078 | Verify DO Transaction functionality for Profit Withdraw payout via Cheque | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/CAfJJbH_WV1F https://prnt.sc/cp-m80ezLeHw
|  | TC-079 | Verify search/filter using Shadow Account Number for Profit Withdraw | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/aOqvQDhsW0TY https://prnt.sc/evpxxORcZSEg
|  | TC-080 | Verify the error handling when searching with a unique, non-existent, or mismatched record combination for Profit Withdraw. | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/61UBedHU4yDh
|  | TC-081 | Verify Stop Payment for selected records. | UI | [5 empty] | PASS |  |  |  | https://prnt.sc/JznJE0TFz8VB https://prnt.sc/nCCqn9aypei_

## Data Preparation Combination(18
SL NO | Event Type | Payment Method | Shadow Account No | Account No
1 | Fixed Deposit Closing | BEFTN | 1. 0025020000268 2. 0023010000208 | 1. 0021110000094 2. 0021010000574
2 | Fixed Deposit Closing | RTGS | 1. 0025020000268 2. 0025020000011 | 1. 0021110000102 2. 0027110000026
3 | Fixed Deposit Closing | Transfer | 1. 0025020000268 2. 0023010000208 | 1. 0021110000119 2. 0021110000144
4 | Fixed Deposit Closing | Cheque | 1. 0025020000268 2. 0025020000011 | 1. 0021110000128 2. 0024020000063
5 | Fixed Deposit Closing | Pay Order | 1. 0025020000268 2. 0023010000208 | 1. 0021110000136 2. 0027110000034
6 | Recurring Deposit Closing | BEFTN | 1. 0023010000208 2. 0023010000208 | 1. 0022220000081 2. 0027770000126
7 | Recurring Deposit Closing | RTGS | 1. 0023010000208 2. 0025020000268 | 1. 0022220000099 2. 0027770000084
8 | Recurring Deposit Closing | Transfer | 1. 0025020000086 2. 0025020000268 | 1. 0022140000269 2. 0027770000118
9 | Recurring Deposit Closing | Cheque | 1. 0023010000208 2. 0025020000268 | 1. 0027770000076 2. 0027770000092
10 | Recurring Deposit Closing | Pay Order | 1. 0025020000094 2. 0025020000268 | 1. 0022110000068 2. 0027770000109
11 | Withdrawal Advice | BEFTN | 1. 0025020000268 2. 0023010000208 | 1. 0021010000566 2. 0027110000018
12 | Withdrawal Advice | RTGS | 1. 0023010000208 2. 0025020000268 | 1. 0021010000566 2. 0027110000018
13 | Withdrawal Advice | Transfer | 1. 0025020000268 2. 0023010000208 | 1. 0021010000566 2. 0021010000566
14 | Withdrawal Advice | Cheque | 1. 0023010000208 2. 0025020000268 3. 0025020000268 4. 0025020000268 | 1. 0021010000566 2. 0021010000566 3. 0027110000018 4. 0027110000018
15 | Withdrawal Advice | Pay Order | 1. 0023010000208 2. 0025020000268 | 1. 0021010000566 2. 0027110000018
16 | CASA Refund | BEFTN |  | 1. 0025020000409 2. 0023010000026
17 | CASA Refund | RTGS |  | 1. 0023010000208 2. 0023010000067
18 | CASA Refund | Transfer |  | 1. 0023010000109 2. 0025020000052
19 | CASA Refund | Cheque |  | 1. 0025020000169 2. 0023010000018
20 | CASA Refund | Pay Order |  | 1. 0025020000268 2. 0023010000083
21 | Investment Disbursement | RTGS | 1. 0023010000083 2. 0025020000011 3. 0025020000094 | 1.0022020000307 2. 0022030000123 3. 0025070000044 4. 0025070000051
22 | Investment Disbursement | Cheque | 1. 0023010000083 2. 0025020000409 | 1. 0026660000097 2. 0025050000113
23 | Investment Disbursement | Pay Order | 1. 0025020000409 | 1. 0025050000121
24 | Investment Disbursement | BEFTN | 1. 0025020000409 | 1. 0025050000139
24 | Profit Withdraw (Auto renewal) | BEFTN | 1. 0025020000268 2. 0023010000208 | 1. 0027110000042 2. 0027110000091
25 | Profit Withdraw | RTGS | 1. 0025020000268 2. 0023010000208 | 1. 0027110000059 2. 0027110000109
26 | Profit Withdraw | Transfer | 1. 0025020000268 2. 0025020000219 | 1. 0027110000067 2. 0027110000117
27 | Profit Withdraw | Cheque | 1. 0025020000268 2. 0023010000208 | 1. 0027110000075 2. 0027110000125
28 | Profit Withdraw | Pay Order | 1. 0025020000268 2. 0023010000208 | 1. 0027110000083 2. 0027110000133
29 | Profit Withdraw(Encashment) | BEFTN | 1.0025020000409(profit) 2. 0025020000268(encash) | 1. 0027110000141
30 |  | RTGS | 1. 0025020000409 2. 0025020000268 | 1. 0027110000158
31 |  | Transfer |  | 1. 0027110000166
32 |  | Cheque |  | 1. 0027110000174
33 |  | Pay Order |  | 1. 0027110000182
1. 0027110000199
1. 0027110000208
|  | Full balance |  | 1. 0027110000216
|  | Cheque(Other Amount) |  | 1. 0027110000224
|  | Transfer |  | 1. 0027110000232
RTGS
|  | BEFTN |  | 1. 0027110000257