## 18605
Product Name |  | ABABIL NG | TC Start Date |  |  | TC Execution Start Date |  |  |  | TEST CASE STATUS |  | Severity |  | Priority
Event Name |  |  | TC End Date |  |  | TC Execution End Date |  |  |  | PASS | 23 | Critical | 0 | High | 0
Para Form Name |  | Enable Freeze/Unfreeze and Special Instruction Access for MTDR and SSP Accounts (excluding Closed Accounts) | Test Case Developed By | Jannat | [5 empty] | FAIL | 5 | High | 0 | Medium | 0
Developer Name (TL) |  |  | Test Case Reviewed By | Mahbub Hossain | [5 empty] | NT | 0 | Medium | 0 | Low | 0
Test Executed by |  |  | MITS ID | 18605 | [5 empty] | TOTAL | 28 | Low | 0 | Issue Accepted | 0
Req ID | Requirement Description | TC ID | Test Case Description | Category | Automation TC ID | Test Steps | Test Data | Expected Result | Actual Result | QA Status | Tested By | Severity | Priority | QA Remarks | Dev Status | Developed By | Dev Remarks | Updated QA Status (1/12/2025) | Updated QA Status | Updated QA Status (4/12/2025) Env-13 | Updated QA Status | Updated QA Status (4/12/2025) Env-11 | Updated QA Status
|  | TC_01 | Verify user can add Special Instruction for Active CASA account | UI |  | 1. Search an Active CASA account 2. Open account details 3. Click “Special Instruction” option 4. Enter a new instruction 5. Save | 1. Active CASA Account: 1120000000509 2. Select Special Instruction Type: Cheque stop 3.Cheque Number from: XYZ6000004 4. Cheque Number to: XYZ6000007 | Special Instruction should successfully saved and displayed in the account. | Special Instruction is successfully saved and displayed in the account. | PASS |  |  |  | https://prnt.sc/LU_qj76huys3 https://prnt.sc/mWcn6BnW7dRG |  |  |  | PASS | https://prnt.sc/0dC0Lrh7F-kx | PASS | https://prnt.sc/tOegu66YwDAp https://prnt.sc/BRjqphf2BOul | PASS | https://prnt.sc/ZgNZtBuvDrxN https://prnt.sc/q0LHX2czu21h
|  | TC_02 | Verify user can withdraw existing Special Instruction for Active CASA account | UI |  | 1. Search an Active CASA account with existing Special Instruction 2. Open Special Instruction screen 3. Click withdraw button 4. show confirmation message:Y/N | 1.Withdraw special instruction reason:Exposed 2. Confirmation messgae: Y | System should withdraw sucessfully. | Success! Special instruction withdrawn successfully | PASS |  |  |  | https://prnt.sc/pMe3yrk635ku https://prnt.sc/gMdQEaRCXTUS |  |  |  | PASS | https://prnt.sc/l_29-BZ7K7J1 https://prnt.sc/K7xd33fzTD1J | PASS | https://prnt.sc/ovndbmPACIFJ | PASS | https://prnt.sc/HNTHE8DMfFOG https://prnt.sc/rgg1kj57s3o_
|  | TC_03 | Verify proper error message displayed when attempting Special Instruction action on same Instruction type action | UI |  | 1. Search an Active CASA account 2. Open account details 3. Click “Special Instruction” option 4. Enter a new instruction 5. Save | 1. Active CASA Account: 1120000000584 2. Select Special Instruction Type: No Transaction 3.Description: No Transaction | Should show proper error message | As expected | PASS |  |  |  | https://prnt.sc/rwLznFOtTLPW https://prnt.sc/sXKISh45hZSd |  |  |  | PASS | https://prnt.sc/z3jXCNHD9GoW | PASS | https://prnt.sc/rBHuYHbrddaq | PASS | https://prnt.sc/ISYEmW93BNUR
|  | TC_04 | Verify user can add Special Instruction for Dormant CASA account | UI |  | 1. Search a Dormant CASA account 2. Open account details 3. Click “Special Instruction” 4. Add new instruction 5. Save | Account Status: Dormant | Special Instruction should successfully saved. | Error! DORMANT. This action can't be performed on DORMANT account. | FAIL |  |  |  | https://prnt.sc/6vcGLrri6QYs https://prnt.sc/sNt2bGlGpnG8 |  |  |  | PASS | https://prnt.sc/dPRGVe74JlVi https://prnt.sc/D807ngjhspwF | PASS | https://prnt.sc/N1JCpJ42NwHo | PASS | https://prnt.sc/XFoNGoj1XxYY https://prnt.sc/K1Y4vNCL5uBP
|  | TC_05 | Verify user can withdraw existing Special Instruction for Dormant CASA account | UI |  | 1. Search a Dormant CASA account with existing Special Instruction 2. Open Special Instruction screen 3. Edit instruction 4. Save | Account Status: Dormant | Withdraw Special Instruction should saved and displayed. | Error! Account not activated exception. | FAIL |  |  |  | https://prnt.sc/15sXu2B93org |  |  |  | FAIL | https://prnt.sc/-AJpgQDqicFg https://prnt.sc/SngUlDc7tp06 | PASS | https://prnt.sc/1xgKfw4oIE0x https://prnt.sc/DT38_3fUvyO6 | PASS | https://prnt.sc/Qn6VwKSDBd8t https://prnt.sc/XxUfiOiBhREh
|  | TC_06 | Ensure Special Instruction option is available for Inactive CASA accounts | UI |  | 1. Search CASA accounts with statuses: Inactive 2. Open each account detail screen | Account Status: Inactive | Special Instruction option should be visible & enabled | Special Instruction option is visible & enabled | PASS |  |  |  | https://prnt.sc/6O3g_oh4Q6tk https://prnt.sc/HYxblQDbYRnS |  |  |  | PASS | https://prnt.sc/gwc1qg8gUouK https://prnt.sc/9gW-fcqKZhuW | PASS | https://prnt.sc/ESqvTTwQ2j1S https://prnt.sc/2hKxsFcyNHbr | PASS | https://prnt.sc/556khRyzEc4J https://prnt.sc/E51786EJhSm9
|  | TC_07 | Verify user can withdraw existing Special Instruction for Inactive CASA account | UI |  | 1. Search an Active CASA account with existing Special Instruction 2. Open Special Instruction screen 3. Click withdraw button 4. show confirmation message:Y/N | 1. Account Status: Inactive 2.Withdraw special instruction reason:Exposed 3. Confirmation messgae: Y | Special instruction should withdrawn | Special instruction withdrawn successfully | PASS |  |  |  | https://prnt.sc/h_F4FMtQR9SG |  |  |  | PASS | https://prnt.sc/PGZedPSFN6l6 https://prnt.sc/mSqajR1nuQmy | PASS | https://prnt.sc/6ZTIrPdAWQuf https://prnt.sc/yqRhDh235I3e | PASS | https://prnt.sc/dMaOt63l0lO6 https://prnt.sc/aNb172fv-vd9
|  | TC_08 | Ensure any Special Instruction icon/indicator is hidden for Closed CASA account | UI |  | 1. Search Closed account 2. Navigate to account summary listing 3. Verify Special Instruction indicator is not displayed | Account Status: Closed | No Special Instruction icon should appear for Closed accounts. | No Special Instruction icon is appear for Closed accounts. | PASS |  |  |  | https://prnt.sc/GmllTsTjXco5 |  |  |  | PASS | https://prnt.sc/8QoZVezquFUb https://prnt.sc/Xf_Y0COELX1T | PASS | https://prnt.sc/RvFpWe7TD9nc | PASS | https://prnt.sc/VZ9_kU75t_kI
|  | TC_09 | Verify system shows error when user attempts Special Instruction action for Closed account | Negative |  | 1. Navigate to Activated CASA Account Special Instruction UI. 2. Select “Close Account” option. 3. Enter the Account ID in the Account ID field. 4. Click on “Submit” or equivalent action button. | Account No:1180000000099 Account ID: 5288 Account Status: Closed | System must prevent action and display appropriate message: Action not allowed. Account is closed. | Error! CLOSED. This action can't be performed on CLOSED account. | PASS |  |  |  | https://prnt.sc/2-8GBvcyhlKf |  |  |  | PASS | https://prnt.sc/Ku4HJHxR45og | PASS | https://prnt.sc/pRgD8N1TMYEb | PASS | https://prnt.sc/_4POCB2_4mim
|  | TC_10 | Verify error message when user attempts to force open Special Instruction via URL for Closed CASA account | Negative |  | 1. Copy valid URL for Special Instruction 2. Replace account number with a Closed CASA account number 3. Try to open 4. Observe message | Account Status: Closed | System must display error: “Invalid action. Account is closed.” | CLOSED. This action can't be performed on CLOSED account | PASS |  |  |  | https://prnt.sc/Yk0xRQ-UNUsF |  |  |  | PASS | https://prnt.sc/_FxJg15WdH4r https://prnt.sc/2UtoCU3TWPmc | PASS | https://prnt.sc/5DCJOYVA5PCf https://prnt.sc/HkUROixsdqA8 | PASS | https://prnt.sc/NW5DkIJt1All https://prnt.sc/zeVjlNf490mN
|  | TC_11 | Verify user can Freeze an Active MTDR account | UI |  | 1. Search an Active MTDR account 2. Open Account Details 3. Click Freeze option 4. Enter reason 5. Confirm | Account number: 1976000000075 Account Type: MTDR Status: Active Freeze | System successfully freezes the MTDR account and displays confirmation message | As expected, System successfully freezes the MTDR account and displays confirmation message | PASS |  |  |  | https://prnt.sc/BpUrzgKy0qOs https://prnt.sc/Vd5BBcTuv44N |  |  |  | PASS | https://prnt.sc/4llOPD2qgiCV https://prnt.sc/t-3nL0s4on2G | PASS | https://prnt.sc/19MREcH3ayh- https://prnt.sc/o7w9i1fXMCjZ | PASS | https://prnt.sc/JIJKKSu8PrcP https://prnt.sc/tyiR5ahmxHWr https://prnt.sc/4Gbl9V3wWbCf
|  | TC_12 | Verify user can Unfreeze a Frozen MTDR account | UI |  | 1. Search a Frozen MTDR account 2. Open account details 3. Click Unfreeze 4. Confirm | Account number: 1976000000075 Account Type: MTDR Status: Frozen Unfreeze reason: Customer request | System successfully unfreezes the MTDR account. | As expected, System successfully unfreezes the MTDR account. | PASS |  |  |  | https://prnt.sc/6OGA-NkjgLtT https://prnt.sc/8O87c4hbhA2Z |  |  |  | PASS | https://prnt.sc/4gIFdh2fazHW https://prnt.sc/8GqYQSTSgopB https://prnt.sc/X2iDlTFtyNO_ | PASS | https://prnt.sc/G1s_deiLn2W8 https://prnt.sc/wTEmAtKMfLfH https://prnt.sc/kMxM5dHX1Y5F | PASS | https://prnt.sc/_QhbGAprsFHM https://prnt.sc/9gFTFn-SRhM1
|  | TC_13 | Ensure Freeze/Unfreeze option is available for inactive MTDR |  |  | 1. Search MTDR accounts in statuses: Inactive 2. Verify Freeze/Unfreeze availability | Account number: 1976000000076 Status: Inactive | Freeze/Unfreeze options should visible and enabled. | Freeze/Unfreeze option is Visible and enable | PASS |  |  |  | https://prnt.sc/7uDmeYxLWhaX https://prnt.sc/NzxEbJN75DaD |  |  |  | PASS | https://prnt.sc/ZJ4705WHLnE6 https://prnt.sc/Wxx6mV3ER9hI https://prnt.sc/eCj2mizaEHl5 https://prnt.sc/F0aph93qjF6f | PASS | https://prnt.sc/QXYc99YKamas https://prnt.sc/24pHQ-rJ1pct https://prnt.sc/mLLFgu_RDJ_Y | PASS | https://prnt.sc/zlU8xMZbLExE
|  | TC_14 | Ensure Freeze/Unfreeze option is available and added for Mature MTDR |  |  | 1. Search MTDR accounts in statuses: Mature 2. Verify Freeze/Unfreeze availability |  | Freeze/Unfreeze should added | Freeze/Unfreeze is sucessfully added | PASS | [7 empty] | PASS | https://prnt.sc/PiYA5jKGtPhQ https://prnt.sc/IeSVCQ9hYoOh https://prnt.sc/kSIrIPllVr0n | PASS | https://prnt.sc/xwXllkxN5bDa https://prnt.sc/jdfY2AETV10W | PASS | https://prnt.sc/IXysNE3ZBVOk https://prnt.sc/Of2yB9QVdHFx
|  | TC_15 | Verify user can Unfreeze a Frozen MTDR account in Mature | UI |  | 1. Search a Frozen Mature MTDR accountt 2. Open account details 3. Click Unfreeze 4. Confirm | Account number: 1976000000030 Account Type: MTDR Status: Frozen Unfreeze reason: Customer request | System successfully unfreezes the MTDR account. | As expected, System successfully unfreezes the MTDR account. | PASS | [7 empty] | PASS | https://prnt.sc/w2nor74oa9lz https://prnt.sc/J-JXAoRuu9-w | PASS | https://prnt.sc/V2mMqFJ4lIxA https://prnt.sc/LYjDW72vNSdF | PASS | https://prnt.sc/2UU5oL87nPmZ https://prnt.sc/1Pn4_LABVdmZ
|  | TC_16 | Verify user can Freeze an Inactive MTDR account | UI |  | 1. Search an Inactive MTDR account 2. Open Account Details 3. Click Freeze option 4. Enter reason 5. Confirm | Account number: 1976000000076 Account Type: MTDR Status: Inactive | System successfully freezes the MTDR account and displays confirmation message | As expected, System successfully freezes the MTDR account and displays confirmation message | PASS |  |  |  | https://prnt.sc/zdBJZOdocIhf https://prnt.sc/3FAlKdoldOKX https://prnt.sc/8Q5BOTQICGsc |  |  |  | PASS | https://prnt.sc/F0aph93qjF6f | PASS |  | PASS | https://prnt.sc/Oftu9DujdANd https://prnt.sc/IrbwIpnoULmj
|  | TC_17 | Verify user can Unfreeze a Frozen MTDR account in Inactive | UI |  | 1. Search a Frozen Inactive MTDR accountt 2. Open account details 3. Click Unfreeze 4. Confirm | Account number: 1976000000030 Account Type: MTDR Status: Frozen Unfreeze reason: Customer request | System successfully unfreezes the MTDR account. | As expected, System successfully unfreezes the MTDR account. | PASS | [7 empty] | PASS | https://prnt.sc/w2nor74oa9lz https://prnt.sc/J-JXAoRuu9-w | PASS | https://prnt.sc/eVAy7dg_hYac https://prnt.sc/RN0-AlkAwOX1 https://prnt.sc/NdIwiMxjRlDW | PASS | https://prnt.sc/OFegqlzyT4Ay https://prnt.sc/Is8HFIapjD81 https://prnt.sc/3Fni3FGngall
|  | TC_18 | Verify Freeze/Unfreeze option is hidden or disabled for Closed MTDR accounts |  |  | 1. Search a Closed MTDR account 2. Open account details 3. Observe Freeze/Unfreeze option | Account Type: MTDR Status: Closed | Freeze/Unfreeze button should be hidden or disabled. | Freeze/Unfreeze button is hidden. | PASS |  |  |  | https://prnt.sc/PbhKInlrbm9N |  |  |  | PASS | https://prnt.sc/v5ku1IWnZAe5 | PASS | https://prnt.sc/W1HYe5c4ERFS | PASS | https://prnt.sc/AF1gOF6CQ2Ph
|  | TC_19 | Verify system displays proper error message when user attempts Freeze/Unfreeze action on a Closed MTDR account | Negative |  | 1. Search a Closed MTDR account 2. Click Freeze/Unfreeze option (if visible) 3. Try direct URL access for Freeze/Unfreeze or Special Instruction 4. Observe system response | Account Number: 1351000000052 Account Type: MTDR Status: Closed with balance | System must prevent action and display appropriate message: “Action not allowed. Account is closed.” | Error! CLOSED account is not freezeable. The system allows to reach the final confirmation step of the 'Impose Freeze' UI. expect the error message, 'CLOSED account is not freezeable,' to be displayed only after clicking the confirmation button. | FAIL |  |  |  | https://prnt.sc/xkRUfivkiOiY |  |  |  | PASS | https://prnt.sc/yX9MbLlMyUCF | PASS | https://prnt.sc/hHTXUZl7PSKc | PASS | https://prnt.sc/baqkURxqWTKn
|  | TC_20 | Verify user can Freeze an Active SSP account |  |  | 1. Search an Active SSP account 2. Open Account Details 3. Click Freeze option 4. Enter reason 5. Confirm | Account number: 1320000000067 Account Type: SSP Status: Active | System successfully freezes the SSP account and displays confirmation message | As expected, System successfully freezes the SSP account and displays confirmation message | PASS |  |  |  | https://prnt.sc/3Aylbhp2ffu6 https://prnt.sc/RV5Y83eJ_wzO |  |  |  | PASS | https://prnt.sc/J3M4BlLpBrf7 https://prnt.sc/HCX8TYPx3GkB | PASS | https://prnt.sc/V057Tzh6Bwj9 https://prnt.sc/gC5tonn__Qyq | PASS | https://prnt.sc/BzM6A_O7aXXM https://prnt.sc/2F0Hesp_55QJ
|  | TC_21 | Verify user can Unfreeze a Frozen SSP account | UI |  | 1. Search a Frozen SSP account 2. Open account details 3. Click Unfreeze 4. Confirm | "Account number: 1320000000067 Account Type: SSP Status: Frozen Unfreeze reason: Customer request | System successfully unfreezes the SSP account. | As expected, System successfully unfreezes the SSP account. | PASS |  |  |  | https://prnt.sc/gQLQrkygnTWl |  |  |  | PASS | https://prnt.sc/54nMFUdHEQsX | PASS | https://prnt.sc/BdGBv4um6XOv | PASS | https://prnt.sc/MiLXyuV9Yu82 https://prnt.sc/Hny50UvrExiu
|  | TC_22 | Ensure Freeze/Unfreeze option is available for Inactive SSP | UI |  | 1. Search MTDR accounts in statuses: Inactive 2. Open each account 3. Verify Freeze/Unfreeze availability | Account number: 1352000000018 Status: Inactive | Freeze/Unfreeze options should visible and enabled for inactive account. | Freeze/Unfreeze option is Visible and enable | PASS |  |  |  | https://prnt.sc/l0CKyYsVzIOq https://prnt.sc/Wk44KuDGRwtc https://prnt.sc/eG15p9R7UfMI |  |  |  | PASS | https://prnt.sc/zIkpwlyY9mXY https://prnt.sc/zIkpwlyY9mXY https://prnt.sc/ZDxCVwDqRBPC | PASS | https://prnt.sc/R-a2bgvW-x_y https://prnt.sc/5KWhDxa9iVcT https://prnt.sc/1dfzV5yEOqzR | PASS | https://prnt.sc/YTeJ4omvmxir https://prnt.sc/ly5mhC6HO4hB https://prnt.sc/sJncuC9Jrvvl
|  | TC_23 | Verify user can Unfreeze a Frozen SSP account in Inactive | UI |  | 1. Search a Frozen Inactive SSP accountt 2. Open account details 3. Click Unfreeze 4. Confirm | Account Type: SSP Status: Frozen Unfreeze reason: Customer request | System successfully unfreezes the SSP account. | As expected, System successfully unfreezes the SSP account. | PASS | [7 empty] | PASS | https://prnt.sc/8y1KsiE6e1Tc https://prnt.sc/99WW-euOSbsk | PASS | https://prnt.sc/2S4xbwv38WJp https://prnt.sc/OvPy0bYQojsE | PASS | https://prnt.sc/SULAniWpyt-8 https://prnt.sc/fq-EaOImFiLW
|  | TC_24 | Verify Freeze/Unfreeze option is hidden or disabled for Closed SSP accounts | UI |  | 1. Search a Closed SSP account 2. Open account details 3. Observe Freeze/Unfreeze option | Account number: 1351000000052 Account Type: SSP Status: Closed | Freeze/Unfreeze button should be hidden or disabled. | Freeze/Unfreeze button is hidden. | PASS |  |  |  | https://prnt.sc/cYyi8SxyB9Pa |  |  |  | PASS | https://prnt.sc/er6mcJif-FtF | PASS | https://prnt.sc/66n-F7aXF-K3 | PASS | https://prnt.sc/MiOENzl46EMi
|  | TC_25 | Verify system displays proper error message when user attempts Freeze/Unfreeze action on a Closed SSP account | Negative |  | 1. Search a Closed MTDR account 2. Click Freeze/Unfreeze option (if visible) 3. Try direct URL access for Freeze/Unfreeze or Special Instruction 4. Observe system response | Account Number: 1351000000052 Account Type: SSP Status: Closed with balance 0 | System must prevent action and display appropriate message: “Action not allowed. Account is closed.” | Error! CLOSED account is not freezeable. The system allows to reach the final confirmation step of the 'Impose Freeze' UI. expect the error message, 'CLOSED account is not freezeable,' to be displayed only after clicking the confirmation button. | FAIL |  |  |  | https://prnt.sc/cKbvdfEWTofp https://prnt.sc/nCIPPPo8PXbI |  |  |  | PASS | https://prnt.sc/LnYYufvupQnG | PASS | https://prnt.sc/StJVxRXGIbVo | PASS | https://prnt.sc/s1BqarNMEPhh
|  | TC_26 |  | Negative |  | 1. Search a Closed MTDR account 2. Click Freeze/Unfreeze option (if visible) 3. Try direct URL access for Freeze/Unfreeze or Special Instruction 4. Observe system response | Account Number: 1976000000078 Account Type: SSP Status: Closed with balance | System must prevent action and display appropriate message: “Action not allowed. Account is closed.” | Error! CLOSED account is not freezeable. The system allows to reach the final confirmation step of the 'Impose Freeze' UI. expect the error message, 'CLOSED account is not freezeable,' to be displayed only after clicking the confirmation button. | FAIL |  |  |  | https://prnt.sc/wCA2k9SgkVSG |  |  |  | PASS | https://prnt.sc/8tNTKflApA8Y | PASS | https://prnt.sc/WGn6DirPJIzt | PASS | https://prnt.sc/OikzRqyrXXyX
|  | TC_27 | Ensure Freeze/Unfreeze option is available and added for Mature SSP |  |  | 1. Search SSP accounts in statuses: Mature 2. Verify Freeze/Unfreeze availability and created |  | Freeze/Unfreeze should added | Freeze/Unfreeze is sucessfully added | PASS |  |  |  | https://prnt.sc/C0y6y2pubZ_s |  |  |  | PASS | https://prnt.sc/guP2QGhAwG8I https://prnt.sc/pZ4l3x3jVas7 https://prnt.sc/ZHqjB_dPYGbA | PASS | https://prnt.sc/_Y6ufZsJT95C https://prnt.sc/RcHHRmZRG7Pa https://prnt.sc/MArxRD99x8oA | PASS | https://prnt.sc/33Ya7Squk8K5 https://prnt.sc/IVtWTnOJ9zFC
|  | TC_28 | Verify user can Unfreeze a Frozen SSP account in Mature | UI |  | 1. Search a Frozen Mature SSP accountt 2. Open account details 3. Click Unfreeze 4. Confirm | Account Type: SSP Status: Frozen Unfreeze reason: Customer request | System successfully unfreezes the SSP account. | As expected, System successfully unfreezes the SSP account. | PASS | [7 empty] | PASS | https://prnt.sc/UFnBei0knC4E https://prnt.sc/pYRErAmQNz4m | PASS | https://prnt.sc/XQ4x_Yr6eiXo https://prnt.sc/KdXa7g_qKoZp | PASS | https://prnt.sc/m9dRVgPx09lO https://prnt.sc/hJ82-epwwr9v